## Tabelle1
ML-Tasks | Status | Done-Date | Deadline | Comment
Creat Git Team-B | Done | 2025-05-02 | 2025-05-02
Identify scenarios : • Identify requirements • Identify timing behaviour | Done | 2025-05-06 | 2025-05-08
Model all scenarios using SysML / UML | Done
Identify required (Signals / Events Modeled) | Done | 2025-05-07 |  | merge_request - merge_ack - open_gap - start_merge - merge_done
Identify Data Modeled (as variables) | Done |  |  | Merge intent as (merge_request) - Gap readiness as (gap_ready) - Timing guarantees as (Clocks (t)) - Safe timing windows as (MAX_*_TIME)
Specify an appropriate protocol for scenario | Done
Use Timed Automata and UPPAAL | pending |  |  | Error
A.A presentation | Tbd |  | Tbd